## BUDGET PLAN 15-16-FIN
Plan for the Year 2015-16
Product : Electrical Machines
| (* represents Spill Over from 14-15) (# represent project on hold) | [11 empty] | PLAN |  |  |  | R0-02.04.15
DESCRIPTION | FIRST QUARTER |  |  | SECOND QUARTER |  |  | THIRD QUARTER |  |  | FOURTH QUARTER |  |  | 195-
| APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | 250 | 270 | 500 | 660 | 700 | 800 | SUM
TG | [12 empty] | 1 | 0 | 3 | 4 | 3 | 1 | 12
800 | FOURTH QUARTER MAR: GDWR-2
3723/4334
600-700 | FIRST QUARTER MAY: LLT-3*; FIRST QUARTER JUN: RAPP-7; SECOND QUARTER JUL: SRGH-8; SECOND QUARTER SEP: RAPP-8; THIRD QUARTER NOV: KAPP-4; FOURTH QUARTER FEB: IBV-2; FOURTH QUARTER MAR: NKRN-2 |  | TG |  | 12
| FIRST QUARTER MAY: 4694/5116; FIRST QUARTER JUN: 5881/6845; SECOND QUARTER JUL: 2758/3032; SECOND QUARTER SEP: 5784/6782; THIRD QUARTER NOV: 5203/5901; FOURTH QUARTER FEB: 3684/4173; FOURTH QUARTER MAR: 2500 |  | RT-Q |  | 1
| FIRST QUARTER APR: MDA-Rt-Sp*; FOURTH QUARTER FEB: BARA-RT-Sp; FOURTH QUARTER MAR: RAGR-RT-Sp |  | RT-Sp |  | 6
| 1283 | [9 empty] | 1286 | 2180
500 | FIRST QUARTER APR: VAL-Q-Rt*; FIRST QUARTER JUN: UNHR-6; FOURTH QUARTER JAN: NYLN-1; FOURTH QUARTER MAR: NYLN-2
| 744 |  | 3698/4019 | [6 empty] | 3819/4110 |  | 3819/4110
195-300 | THIRD QUARTER OCT: RLSM-RT-Sp; THIRD QUARTER NOV: OBRA-ST-(Rp)*; FOURTH QUARTER JAN: KRD-R&M
[7 empty] | 2214 | 178 |  | 2412/2701
[10 empty] | TUT-RT-Sp (KWU) | TUT-RT-Sp (Rusian)
[10 empty] | 2250 | 2250
EXCITER | [12 empty] | THRI | 500-600 |  |  | 660-800 |  | SUM
660-800 | LLT-2* | MODA-4* | MODA-3 | RAPP-7 | SGRH-7 | KAPP-4 | SGRH-8 | RAPP-8 | NKRN-1 | IBV-1 | GDWR-1 | GDWR-2 | 1 | 6 |  |  | 20 |  | 27
| 436/526 | 475/525 | 548/748 | 1056/1183 | 579/611 | 958/1045 | 522/551 | 1038/1163 | 350 | 694/770 | 519/841 | 519/841
| BARA-2* | MODA-Sp* | KAPP-3* | LLT-3 | BLRY-Rt-Sp | BARA-Sp |  |  |  |  | NKRN-2 | IBV2 NKRN-Sp |  |  | Ex-M |  | 21
| 848/901 | 789 | 815/890 | 547/748 | 366 | 788 |  |  |  |  | 350 | (694/770) + 751 |  |  | Ex-Q |  | 2
500-600 | FIRST QUARTER MAY: CPUR-RT -Sp*; SECOND QUARTER JUL: VAL-Q*; SECOND QUARTER AUG: VND-Sp*; SECOND QUARTER SEP: UNHR-6; THIRD QUARTER OCT: NYLN-1; THIRD QUARTER NOV: NYLN-2 |  |  | Ex-Sp |  | 4
| FIRST QUARTER MAY: 595; SECOND QUARTER JUL: 436/509; SECOND QUARTER AUG: 699; SECOND QUARTER SEP: 442/527; THIRD QUARTER OCT: 393/507; THIRD QUARTER NOV: 393/507 |  |  | Rt-Sp |  | 3
| SECOND QUARTER AUG: RGDM-Rt-Rp*; SECOND QUARTER SEP: JHAZ-Q; THIRD QUARTER NOV: RAI-Rt-Sp |  |  | Rt-Rp |  | 1
[5 empty] | 350 | 430/461 |  | 818
200-270 | SECOND QUARTER JUL: NSIK-5; FOURTH QUARTER MAR: SRN-1 # SRN-2 #
|  |  |  | 248/387 | [7 empty] | 248 + 248
ACG | [13 empty] | THRI | 500 | 660 | 700 | 800 | SUM
800 | FOURTH QUARTER JAN: GDWR-1; FOURTH QUARTER FEB: GDWR-2 |  | 2 | 3 | 5 | 4 | 2 | 16
[10 empty] | 217/451 | 217/451
600-700 |  |  | KAPP-3 | RAPP-7 |  | KAPP-4 | RAPP-8 | NKRN-1 | IBV-1 | NKRN-2 | IBV-2 | NKRN-3 |  |  | SOU |  | 16
|  |  | 338/838 | 373/955 |  | 338/838 | 367/940 | 100 | 172/386 | 100 | 172/389 | 100
500 | SECOND QUARTER AUG: UNHR-6; THIRD QUARTER NOV: NYLN-1; THIRD QUARTER DEC: NYLN-2
| SECOND QUARTER AUG: 110; THIRD QUARTER NOV: 164/372; THIRD QUARTER DEC: 164/372 |  | MAUDA-4 & KRD COMPLETED IN 03/15. NKRN-3 Add IN 15-16.
195-300 | FIRST QUARTER MAY: NASIK-5; SECOND QUARTER JUL: NNGR-4; FOURTH QUARTER MAR: SRN-2 #
|  | 76/146 |  | 73/100 | [7 empty] | 82
Mis. | 15 | 15 | 30 | 50 | 65 | 75 | 75 | 75 | 75 | 251 | 418 | 242 | 1386
TG-Spares-Mis. | 150 | 184 | 400 | 400 | 388 | 212 | 386 | 372 | 500 | 700 | 1464 | 1582 | 6738
ACG-Spares | 50 | 75 | 100 | 150 | 150 | 150 | 150 | 150 | 150 | 175 | 175 | 275 | 1750
TOTAL (Rs. Lacs) | 2242 | 1658 | 530 | 600 | 2128 | 1225 | 2825 | 1693 | 1075 | 3476 | 5943 | 6961 | 30356
Qtr Total (Rs. Lacs) | FIRST QUARTER APR: 4430; SECOND QUARTER JUL: 3953; THIRD QUARTER OCT: 5593; FOURTH QUARTER JAN: 16380 | 30356
Qtr % | FIRST QUARTER APR: 14.5935; SECOND QUARTER JUL: 13.0221; THIRD QUARTER OCT: 18.4247; FOURTH QUARTER JAN: 53.9597 | 100
*- Subject to customer clearance by 11/14 # - Subject to hold lift by 12/14
TG-Spares-Main | 0 | 366 | 0 | 0 | 3112 | 788 | 2214 | 996 | 0 | 2250 | 3536 | 0 | 13262
TG-Spares-Total | 150 | 550 | 400 | 400 | 3500 | 1000 | 2600 | 1368 | 500 | 2950 | 5000 | 1582 | 20000
ACG-Spares | 50 | 75 | 100 | 150 | 150 | 150 | 150 | 150 | 150 | 175 | 175 | 275 | 1750
Budget 15-16 (Rs. Lacs) | FIRST QUARTER APR: FIRST QUARTER; SECOND QUARTER JUL: SECOND QUARTER; THIRD QUARTER OCT: THIRD QUARTER; FOURTH QUARTER JAN: FOURTH QUARTER
| APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
TG Main | 0 | 0 | 9579 | 2758 | 0 | 5784 | 0 | 5203 | 0 | 3700 | 2500 | 9923 | 39447
TG Balance | 3 | 538 | 447 | 978 | 257 | 2 | 999 | 39 | 666 | 0 | 56 | 3155 | 7140
Ex Main | 549 | 0 | 1419 | 1304 | 513 | 958 | 1022 | 1538 | 350 | 650 | 869 | 1664 | 10836
Ex Balance | 200 | 85 | 267 | 267 | 0 | 178 | 29 | 0 | 35 | 0 | 323 | 441 | 1825
TGS-Main | 0 | 366 | 0 | 0 | 0 | 788 | 2214 | 996 | 0 | 4862 | 3536 | 2931 | 15693
TGS-Bal. | 150 | 184 | 400 | 400 | 550 | 550 | 386 | 372 | 500 | 700 | 1464 | 2331 | 7987 | Include 34 Cr anticipated orders
TGS-Total | 150 | 550 | 400 | 400 | 550 | 1338 | 2600 | 1368 | 500 | 5562 | 5000 | 5262 | 23680
BK-1 Total | 902 | 1173 | 12112 | 5707 | 1320 | 8260 | 4650 | 8148 | 1551 | 9912 | 8748 | 20445 | 82928
ACG Main | 0 | 74 | 338 | 449 | 110 | 338 | 367 | 200 | 300 | 367 | 317 | 232 | 3092
ACG Bal. | 122.4 | 94 | 464 | 607 | 190 | 243 | 51 | 573 | 153 | 81 | 247 | 517 | 3342.4
ACG Spares | 50 | 75 | 100 | 150 | 150 | 150 | 150 | 150 | 150 | 175 | 175 | 275 | 1750 | Include 2.5 Cr anticipated orders
BK-4 Total | 172.4 | 243 | 902 | 1206 | 450 | 731 | 568 | 923 | 603 | 623 | 739 | 1024 | 8184.4
EM Total (BE) | 1074.4 | 1416 | 13014 | 6913 | 1770 | 8991 | 5218 | 9071 | 2154 | 10535 | 9487 | 21469 | 91112.4
Qtr Sum | FIRST QUARTER APR: 15504.4; SECOND QUARTER JUL: 17674; THIRD QUARTER OCT: 16443; FOURTH QUARTER JAN: 41491 | 91112.4 | LE = 89046
% of Annual Budget | FIRST QUARTER APR: 17.0168; SECOND QUARTER JUL: 19.398; THIRD QUARTER OCT: 18.0469; FOURTH QUARTER JAN: 45.5383 | 100
Note :
1. * - Obra plan is subjected to customer order amendment by Nov-14.
2. # - SRN-1 & SRN-2 plan are subjected to hold lift by Dec-14.
Note on F56: less 6 for mauda-4
Note on M56: less 600 for manuguru-1 & 2 less 27 for mis. To match VC commitment
Note on F57: less 66 for suratgarh-7
Note on F58: less 33 for suratgarh-7
Note on F63: 215 less for Mauda-4
Note on M63: LESS : 200 - MANUGURU-2
Note on B64: 2.6 LESS FOR Suratgarh-7
Note on G64: 124 less for mauda-4
Note on H64: less for suratgarg-7